## Sheet1
	Nazwa	Numer	Quest				Animacja	Custom/Prop	Dialogs	Camera / Ratio	Colliders	Uwagi
			Lewa	Środek	Prawa
	Molo	56	Buzz	Joy + Cherry	Bubba		brak					fishing rod misbehaves
	In front	57	Joy	Buzz	Bubba		brak					reach?
	Trash dirt	58	Joy		Bubba		tak					asynhronous poof? Joy and Bubba cleaning animations?
	Trash ext	59	Scoops	Joy	Bubba		nie					Scoops cannot get closer to broken wall. He stops on red lines. Progress animation doesn' work.
	Fance	60	Scoops?	Joy	Bubba		Nie – a/e					Progress animation doesn' work. Sent Prop Animation Event – activate, exit triggers?
	Broken wall	61	Joy		Scoops		tak			ok		I would like to have Scoops in intro dialog on the right. I tried to set position in Update Character Dialog Panel but it doesn't work. Also I tired to use Update Dialog Characters – I set 2 elements and Element 0 i set to None, but such sollution generates null reference error.
	Apple display	62	Joy	Scoops	Bubba		tak
	Sale	63	Joy	Scoops	Bubba		chyba ok					I would like to have Bubba in intro dialog on the right
	Sidewalk	64	Joy	Scoops	Bubba		Nie – a/e					I would like to have Bubba in intro dialog on the right. Progress animation doesn' work. Sent Prop Animation Event – activate, exit triggers?
		65	Joy	Scoops	Bubba							Scoops starting point.

	Intro 65		Joy		Duncan					ok		ok
	Wall	16	Joy	Scoops	Buzz		walk			ok		ok
	Wall sign	17	Joy	Scoops	Buzz					ok		ok
	Floor	18	Joy	Scoops	Buzz					ok		ok
	Wall art	19	Joy	Scoops	Buzz			nie działa		ok
	Floor – kitchen	20	Joy	Scoops	Buzz					ok		idealne ustawienie przed ladą
	fridge	21	Joy	Scoops	Buzz					ok		nie w tym miejscu co na mapie, ale tam się prop zmienia
	Ex1	22	Scoops	Joy	Buzz					ok		should be in same place as in 23
	Ex2	23	Scoops	Joy	Buzz					ok		Proposal version. Buzz circles buzz closses his eyes, scoops Chat Bubble
	Ex3	24	Scoops	Joy	Buzz					ok		Buzz "Clipboard_TakeNotes" animation is not working. Could you check that?
	Fishing	25	Buzz		Scoops					ok		Is celebrate okay here?
	Uwagi ogólne											sprawdzić czy wait po admire jest wystarczający

	Counter Back	31	Aggy	Cherry	Duncan					ok		Cherry wynika z poprzedniego questu
	Table	32	Aggy	Cherry	Duncan					ok		ok
	Counter Back x 2	33	Aggy	Cherry	Duncan		walk			ok		chery idzie obok odwraca się plecami a potem do reszty jak już ok
	Chairs	34	Aggy	Cherry	Duncan		cherry dance			ok
	Be cool	35	Aggy	Cherry	Duncan		cloud			ok		jeszcze przeciwsłoneczne i donut

	Intro Region 20	Intro	Dunacan				nic	brak	ok	ok
	Video Equip	56	Camera	Joy	Duncan		Walk, 3 cams	brak	ok	ok
	Weeds	57	Camera	Joy	Duncan		clean	nie jak powinno	ok	ok
	Deck Trash	58	Camera	Joy	Duncan		poof, clean	nie jak powinno	ok	ok	ok
	Deck Boxes	59	Camera	Joy	Duncan		clean	nie jak powinno	ok	ok	ok
	Path Crosfade	60	Camera	Joy	Duncan		look arround	nie działa	ok	ok
	Deck Crosfade	61	Camera	Joy	Duncan		look arround	nie jak powinno	ok	ok
	Tables	62	Camera	Joy	Duncan		admire	działa	ok	ok
	Umbrelas	63	Camera	Joy	Duncan		admire	działa	ok	ok
	Chairs	64	Camera	Joy	Duncan		admire, camera man movement	działa	ok	ok	ok
	Reality Show	65	Camera		Duncan		nic	brak	ok	ok

	Interview: Scoops	81	Camera	Scoops	Duncan		nic	brak	ok	ok	ok	eye patch hamster
	On Air	82	Camera	Joy, Bean + Aggy	Duncan		Aggy walk + poof	progrsssion	ok	ok	ok
	Add cameras	83	Camera	Joy + Bean	Duncan		look at	progrsssion	ok	ok	ok
	Nerves	84	Joy		Bean		walk	brak	ok	ok
	Interview: Joy	85	Camera	Joy	Duncan		Joy stratle	brak	ok	ok	ok
75
	Ch 75 Intro	Intro	Joy					brak	ok	ok	ok
	Clean up shop	816	Joy	Pirate	Aggy		poof, clean	progres – njp	ok	ok	ok
	Swap Deck	817	Joy		Pirate			progres	ok	ok	ok
	Walls	818	Joy		Bean		admire, upset, concern	quest	ok	ok	ok
	Floor Main	819	Joy		Bean		dance, upset, phone	quest	ok	ok	ok
	Floor Kitchen	820	Joy		Bean		dance, upset, phone	quest	ok	ok	ok
	Aggy Idea	821	Joy	Bean	Aggy		walk	brak	ok	ok	ok
	Tables	822	Joy		Bean			quest	ok	ok	ok
	Chairs	823	Joy		Bean			quest	ok	ok	ok
	Grand gesture	824	Joy		Bean		blueprint, cheering	character	ok	ok	ok
	Double date	825	Joy	Bean + Pirate	Aggy		bean blueprint	decorations nd	ok	ok	ok
74
	R21 Intro	Intro								ok
	Beach meeting	806								ok
	Arrival	807					pan around – obszar			ok
	Left garden	808								ok	ok
		809								ok	ok
		810								ok
		811								ok	ok
		812								ok	ok
		813								ok	ok
		814								ok	ok
		815								ok
76
	Ch 76 Intro	Intro	Joy		Bean				ok	ok	ok
	Rug 1	826	Cherry		Buzz		cherry walks in, dizzy	progres	ok	ok	ok
	Rug 2 Kitchen	827	Dunacan		Buzz		working, dun tap	progres	ok	ok	ok
	Display	828	Buzz		Cherry		look at	quest	ok	ok	ok	cherry może się czymś zająć – aktualnie gada, ale może powinna pracować?
	Wall art	829	Buzz		Duncan		look at	progres	ok	ok	ok	dependency
	Round Counter	830	Buzz		Cherry		Swoosh + poof/work	progres	ok	ok	ok	dependency
	Decorate Counters	831	Buzz	Cherry	Duncan		work, look arround	progres	ok	ok	ok
	Wall Display	832	Buzz	Cherry	Duncan		look at	quest	ok	ok	ok
	Cultist rug	833	Buzz		Cherry		look at	quest	ok	ok	ok	there should be dependency check?
	Supplies	834	Buzz	Cherry	Duncan		buzz clip	Anim – nd	ok	ok	ok	Animation doesn't work or I configurred sth wrong. There should be dependency check?
	Sign	835	Buzz	Cherry + Joy	Duncan		Joy poof	quest	ok	ok	ok
79
	R 22 Intro	Intro		Joy			phone	brak	ok	ok	ok	Not exactly sure where to put Joy, should I add other characters from 855?
	Dock	856	Joy	Aggy	Spree		walks in	brak	ok	ok	ok	Mayby I should leave only 2nd camera?
	Bar	857	Joy	Aggy	Spree		walk sequence? Lada, krzesła, logo?	brak	ok	ok	ok
	Deck	858	Joy	Aggy	Spree		crossfade	progres	ok	ok	ok
	Clean deck part 1	859	Joy	Aggy	Spree		poof, clean? , look at coin?	progres	ok	ok	ok	dependency
	Clean deck part 2	860	Joy	Aggy	Spree		poof, clean?	progres	ok	ok	ok	dependency
	Clean deck part 3	861	Joy	Aggy	Spree		clean	progres	ok	ok	ok	dependency
	Coin	862	Joy	Aggy	Spree		just celebrte	brak	ok	ok	ok
	Fence	863	Joy	Aggy	Spree		look at	progres	ok	ok	ok	Progress animation doesn' work when I use Send Prop Animation event, but it works somehow when I use Refresh Progression Quest Item
	Fence Lights	864	Joy	Aggy	Spree		pan	progres, fill	ok	ok	ok	Fill animation doesn't work. I don't know where to put them and on what they should look at.
	Tiki	865	Joy	Aggy	Spree		look at	progres	ok	ok	ok	Progress animation doesn' work when I use Send Prop Animation event, but it works somehow when I use Refresh Progression Quest Item
81
	Ch 81 Intro	Intro		Spree				brak	ok	ok	ok
	Encounter pirates	876	Spree	Crew	Scoops		poof sequence	brak	ok	ok	ok	used Pfx_Map_Character_Smoke_Poof_01 because I think it fits better to pirates
	Escape	877	Spree		Scoops			brak	ok	ok	ok	Proposal version. Exit (no nav colliders) should be where doors are not on back? On back there are no bars in cage.
	Canon	878	Spree		Scoops		cannon	progres tap	ok	ok	ok	Dependency, if it is possible please move coconuts to lower later so crewmate 2 would be fully visible
	Pirates talk	879	Spree		Scoops			brak	ok	ok	ok	dependency
	Plundering	880	Buzz	Spree	Scoops			tie prop	ok	ok	ok	Proposal version, ties overlap hamsters
	Shipwreak	881	Spree		Scoops		Walk to spit	progres	ok	ok	ok
	Shop roberry	882	Spree		Scoops		walk in and swoosh arround	brak	ok	ok	ok	add look arround after swoosh? Setting defaut Scoops emote to Yarrr doesn't work. I don't know exactly why. Added skip emote reset.
	Cave	883	Spree		Scoops		look at more spit	progres	ok	ok	ok	Dependency. Proposal version: that puddle is quite far from cave. Is is possible to move it closer to the cave so more cave will be visible?
	Loot shoop	884	Spree		Scoops		walk out, cloud (particle)	brak	ok	ok	ok	Dependency – podpiąć
	Feast	885	Spree	Crew	Scoops		feast	in quest prop	ok	ok	ok	Chapter reward – podpiąć. Proposal version. I don't know how that in quest prop should work. I don't see such asset as Prop_R22_Pirate_Feast. Refreshing is not working too.
85
	Ch 85 Intro	Intro		Joy				brak	ok	ok	ok	Proposal version – not exactly sure where to put Joy, I would like to put her near entrance but entrance overlaps her (sorting issue)
	Meet Wings – dock	916	Joy		Wings		walk in	brak	ok	ok	ok
	Clean cobwebs	917	Joy	Wings	Bubba		cleaning, walks in	progres nd.	ok	ok	ok	proposal version – one web is still missing (second for Wings)
	Ice sticks	918	Joy	Wings	Bubba		Swoosh	progres nd.	ok	ok	ok
	Wings ideas	919	Joy	Wings	Bubba		talk	brak	ok	ok	ok	Rozstawione pozycje postaci. I would like to put some Bubba animation in Close Dialog Panel but I'm not sure which. I used excite, but with that it is a lot of jumping (chicken is jumping too).
	Cleaning floor	920	Joy	Wings	Bubba		Swoosh (6, 6, 7.5) + poof/work	progres nd.	ok	ok	ok	Dependency. More swooshes. Split send actions for test – still not working prop.
	Bubba ideas	921	Joy	Wings	Bubba		talk	brak	ok	ok	ok	Dependency.
	Help Joy	922	Joy	Wings	Bubba		argue	brak	ok	ok*	ok	Wings 2d portrait overlapps a little bit Bubba 3d on 4:3. Is that acceptable?
	Walls	923	Joy	Wings	Bubba		look arround	progress	ok	ok	ok	Dependency.
	Floor	924	Joy	Wings	Bubba		look at	progres	ok	ok*	ok	Dependency. Wings 2d portrait overlapps a little bit Bubba 3d on 4:3. Is that acceptable?
	Menu	925	Joy	Wings	Bubba		look at	progres		ok*	ok	Wings 2d portrait overlapps a little bit Bubba 3d on 4:3. Is that acceptable?
86
	Ch 86 Intro	Intro		Wings				brak	ok	ok	ok
	Clean clams – kitchen	926	Joy	Wings	Bubba		jumping!!!	progres nd.	ok	ok	ok	Due to problems mantioned on slack I was not able to check how it looks in 386 and without ability to play quest prefabs I didn't try to configure that quest more. I configured only dialogues and characters.
	Clean clams – bench	927	Joy	Aggy	Wings			progres nd.	ok	ok	ok	Missing colliders for small objects
	Banch	928	Wings	Aggy	Bubba			custom	ok	ok	ok	Dependency, Intro: not sure where put new guest intro, in both dialogues there is nothing about sign
	Wall art	929	Wings	Aggy	Bubba			progrss	ok	ok	ok	dependency
	Booth Tables	930	Wings	Aggy	Bubba			custom	ok	ok	ok	dependency
	Sign	931	Wings	Aggy	Bubba			custom nd.	ok	ok	ok
	Clean – trash	932	Wings	Aggy	Bubba		Swoosh (1,7, 2, 2) + poof/work	progres	ok	ok	ok	Dependency.
	Clean – boxes	933	Wings	Aggy	Bubba		Swoosh (4,2 x2) + poof/work	progres	ok	ok	ok	Dependency.
	Floor	934	Wings	Aggy	Bean			custom	ok	ok	ok
	Rug 1	935	Joy	Wings + Bubba	Aggy			progres	ok	ok	ok	Chapter reward.
87
	Ch 87 Intro	Intro
		936
		937
		938
		939
		940
		941
	Rugs	942	Wings	Bubba	Scoops			progress	ok	ok	ok	proposal
		943
		944
		945										chapter reward
84
		Intro
		906
		907
		908
		909
		910					Swoosh (2,2; 1,9) + poof/work			ok		dependency
		911										dependency
		912
		913					Pan x -0.66, y 43.91
		914					Swoosh (2,5; 2,5) + poof/work
		915										chapter reward
89
	Clams outside	Intro	Joy	Wings + Aggy + Bubba	Bean		scarred	brak	ok	ok	ok
	Investigate patio	956	Wings	Aggy	Bubba		walk out look arround	brak	ok	ok	ok
	Clean clams	957	Wings	Aggy	Bubba		Swoosh (4.5, 4.8, 4)	progres	ok	ok	ok
	Trash	958	Camera	Duncan	Wings		camera movement, swoosh (2.2, 0.8)	progres	ok	ok	ok
	Patio walls	959	Wings	Aggy	Bubba		look arround, pan (9.3, 32.52)	custom	ok	ok	ok
	Clean weeds	960	Camera	Duncan	Wings		Swoosh (2x7, 2x8)	progres	ok	ok	ok	Dependency.
	Choose plants	961	Wings	Aggy	Bubba		look at	custom	ok	ok	ok	Dependency.
	Patio floor	962	Camera	Duncan + Aggy	Wings		work	custom	ok	ok	ok
	Potted trees	963	Camera +Bubba	Aggy + Duncan	Wings			custom	ok	ok	ok	dependency
	Lights	964	Bubba	Aggy + Duncan	Wings			custom	ok	ok	ok	dependency
	Mat	965	Bubba	Aggy + Duncan	Wings			custom	ok	ok	ok	chapter reward, overlap acceptable
90
	Intro	Intro	Wings	Aggy + Bubba	Duncan			brak	ok	ok	ok	I added new waypoint, but finally I put Hamster 2 near existing one so he is not seen in any ratio. Is that okay? Should add camera on 2D or not? Footage is done so I decided to not put camera on 2D, but maybe I should? Wings in in nav colider, I added action to move him in 965 and here. Is that ok?
	Chairs – patio	966	Wings	Aggy	Bubba			custom	ok	ok	ok
	Tables – patio	967	Wings		Bubba			custom	ok	ok	ok
	Bar top	968	Wings		Bubba			custom	ok	ok	ok	Bubba has so little animations, he doesn't even dance
	Supply bar top	969	Wings	Aggy	Bubba		swoosh to center (2.3, 1, 2.1)	progres	ok	ok	ok	dependency
	Bar stools	970	Wings	Aggy	Bubba			custom	ok	ok	ok	dependency
	Invites	971	Wings		Willie/Aggy		willie flies	progres	ok	ok	ok
	Scare Clams	972	Wings	Aggy	Bubba		jumping!!!	progres	ok	ok	ok	dependency
	Laugh Clams	973	Wings	Aggy	Bubba			progres	ok	ok	ok	dependency
	Bribe Clams	974	Joy	Wings + Aggy	Bubba			progres	ok	ok	ok
	Opening	975	Joy	Wings + Bubba	Cherry		Pan (3.45, 40.12702) – 0.67, 41.37	progres	ok	ok	ok	chapter reward
93
	Intro						Screenshake + soundwave		?	ok	ok
	Sothe Clam	996	Joy	Bean	Aggy			tap	ok	ok	ok
		997	Joy		Bean		Pan (16.51, 0.65)	progres	?	ok	ok
		998	Buzz		Bean		Pan (-13.87, -5.69)	progres	?		ok
		999	Joy	Aggy	Bean				?	ok	ok
		1000					Pan (1.374, 11.768); swoosh (2.2, 2.4; 2.5, 3.4)
95
	Intro		Joy		Aggy		Screenshake + soundwave	brak	ok	ok?	ok?	start positions to be modified
	Check clam	1016	Joy		Bean		run	brak	ok		ok	mayby add some clam animation?, mayby poof at start for joy?
	Clean kitchen	1017	Joy		Aggy		Swoosh (3;2.2)	progres	ok	ok?	ok	i dont see where that dirt is – it was visible for short time then dissapeard, swoosh not ready
	Toss old	1018	Joy		Bean		work; swoosh (3.4, 2.8; 2.5, 2.2)	progres	ok	ok	ok	not sure where I should place characters
	Kitchen Floor	1019	Joy		Aggy		look at	custom	ok	ok	ok	dependency
	Display Counter	1020	Joy	Aggy	Bean		look at	custom	ok	ok	ok	dependency
	Display Wall	1021	Joy		Aggy		talk	custom	ok	ok	ok
	Counter Decor	1022	Joy		Bean		work	progres	ok	ok	ok	dependency
	Floor Mat	1023	Joy		Bean		work	custom nd.	ok	ok	ok	dependency
	Clear Clams	1024	Joy	Aggy	Bean		clean	progres	ok	ok	ok	sorting issues with clams in water and characters
	Noise	1025	Joy	Aggy	Scoops + Crew		pirates surprise	brak	ok	ok	ok	chapter reward
97
	Intro		Joy					brak	ok	ok	ok	sorting issues with clams in water and Joy
	Whats wrong	1036	Buzz		Cherry			brak	ok	ok	ok
	Clean clams – kitchen	1037	Buzz		Snack		Swoosh (1.4, 1.7)	progres	ok	ok	ok	i dont see clams, swoosh not fully configurated
	Rug	1038	Buzz		Snack		tap, look arround anims	custom	ok	ok	ok
	Shelves	1039	Buzz		Snack			custom	ok	ok	ok	dependency, sorting issues
	Table	1040	Buzz		Snack			custom?	ok	ok	ok	dependency, where exactly I should place them
	Table	1041	Buzz		Snack			custom	ok	ok	ok
	Shelves	1042	Buzz	Aggy	Snack		swoosh to center (1.5, 0.8, 0.8)	custom	ok	ok	ok	dependency
	Counter	1043	Snack	Buzz	Cherry		cherry walks in	custom	ok	ok	ok	dependency
	Question Cherry	1044	Cherry	Buzz	Aggy			progres	ok	ok	ok
	Investigate candy	1045	Snack	Buzz	Aggy			brak	ok	ok	ok	chapter reward
100
	Intro		Joy	Snack	Scoops		28.54343, 13.74831	brak	ok	ok	ok	I took positions from 1065 but Snack in that quest is walking in and his final position is not always exactly the same as one used by me here.
	Flowers	1066	Joy	Snack	Scoops			custom	ok	ok	ok
	Garden Lights	1067	Joy	Snack	Scoops		look at lights	custom	ok	ok	ok
	Inspection	1068	Joy		Scoops		Swooshes (3.5, 2.8, 4.5)	brak	ok	ok	ok
	Shipwreak	1069	Joy	Snack	Scoops		poof in; nice poof away	brak	ok	ok	ok
	Get Job Back	1070	Joy	Buzz	Scoops		walk in	brak	ok	ok	ok	dependency
	Clam	1071	Snack	Joy	Scoops		poofs	brak	ok	ok	ok	dependency
	Pirate hat	1072	Joy	Snack	Scoops		attachments, removing props using poofs	brak	ok	ok	ok
	First pile	1073	Joy	Snack	Scoops			progres	ok	ok	ok	dependency; prop missbehaves
	Second	1074	Joy	Snack	Scoops			progres	ok	ok	ok	dependency
	Large	1075	Joy	Snack	Scoops			progres	ok	ok	?	chapter reward
103
	Intro		Joy		Bean			brak	ok	?	?	Tylko: take positions from 1095, when you click quest fast, joy talk after shy is very quick even if I add wait (I tried using wait for end of trame too), is that okay or remove that shy trigerr?
	Plan	1096	Joy	Aggy	Scoops		walk in	brak	ok	ok	ok
	Invitation	1097	Scoops	Buzz	Willie		character prop, flying, landing	brak	ok	ok	ok	turned off Scoops talk loop at the begining because his character prop missbehaves during it
	Decorate	1098	Buzz		Aggy		Pan (28.69, 12.84)	progres	ok	ok	ok	dependency, proposal version – waiting for a prop, sotring issue with Buzz and garden
	Flowers	1099	Buzz		Aggy			custom	ok	ok	ok	dependency
	Cameras	1100	Buzz		Duncan		Swoosh (1.8; 4)	progres	ok	?	?	sorting issues with cameras and characters
	Tourches	1101	Joy	Buzz	Scoops		Swoosh (1.5; 1; 2.2)	progres	ok	ok	ok	dependency
	Fountain	1102	Joy	Buzz	Scoops		Swoosh (2; 3.8; 2.2)	custom	ok	ok	ok	dependency; sorting issues – scoops and potted tree, swoosh not fully configurated
	Sweets pile	1103	Joy	Buzz	Scoops			progres	ok	ok	ok	Proposal version: prop not working – not sure where that pile of sweets will be
	Opening	1104		Too many			Pan (26.9461; 15.03036)	brak	ok	ok	ok
	Engagement	1105		Too many			character prop	brak	ok	ok	ok	finish quest – podpiąć